## Project_Info
Field | Value
Project Name | ACME Systems Engineering - Drone Swarm System (Example)
Description | Workbook for team organization, stakeholders, and resource workload tracking.
Owner | Moneypenny (Solution Management)
Version | 1.0
Last Generated | 2025-10-28

## Sprints
Sprint | Start | End | Length (days)
Sprint 1 | 2025-11-03 | 2025-11-16 | 14
Sprint 2 | 2025-11-17 | 2025-11-30 | 14
Sprint 3 | 2025-12-01 | 2025-12-14 | 14
Sprint 4 | 2025-12-15 | 2025-12-28 | 14
Sprint 5 | 2025-12-29 | 2026-01-11 | 14
Sprint 6 | 2026-01-12 | 2026-01-25 | 14
Sprint 7 | 2026-01-26 | 2026-02-08 | 14
Sprint 8 | 2026-02-09 | 2026-02-22 | 14

## Stakeholders
Name | Role | Level | ART | Team | Unit | Influence | Interest | Engagement Plan | Contact
Batman | Product Manager | ART | ART 1 | Team Alpha | Justice League Command | High | High
Superman | Release Train Engineer | ART | ART 1 | Team Alpha | Justice League Command | Medium | High
Wonder Woman | System Architect | ART | ART 1 | Team Alpha | Justice League Command | Medium | High
Iron Man | Scrum Master | ART | ART 1 | Team Beta | Avengers Interface | Medium | High
Captain America | Scrum Master | ART | ART 1 | Team Beta | Avengers Interface | Medium | High
Professor X | Product Manager | ART | ART 2 | Team Alpha | X-Men Flight | High | High
Cyclops | Release Train Engineer | ART | ART 2 | Team Alpha | X-Men Flight | Medium | High
Storm | System Architect | ART | ART 2 | Team Alpha | X-Men Flight | Medium | High
Reed Richards | Scrum Master | ART | ART 2 | Team Beta | Fantastic Four Navigation | Medium | High
Sue Storm | Scrum Master | ART | ART 2 | Team Beta | Fantastic Four Navigation | Medium | High
Raven | Product Manager | ART | ART 3 | Team Alpha | Teen Titans Communication | High | High
Robin | Release Train Engineer | ART | ART 3 | Team Alpha | Teen Titans Communication | Medium | High
Cyborg | System Architect | ART | ART 3 | Team Alpha | Teen Titans Communication | Medium | High
Star-Lord | Scrum Master | ART | ART 3 | Team Beta | Guardians of the Network | Medium | High
Rocket | Scrum Master | ART | ART 3 | Team Beta | Guardians of the Network | Medium | High
Nick Fury | Product Manager | ART | ART 4 | Team Alpha | S.H.I.E.L.D. Security | High | High
Black Widow | Release Train Engineer | ART | ART 4 | Team Alpha | S.H.I.E.L.D. Security | Medium | High
Doctor Strange | System Architect | ART | ART 4 | Team Alpha | S.H.I.E.L.D. Security | Medium | High
Rorschach | Scrum Master | ART | ART 4 | Team Beta | Watchmen Intrusion | Medium | High
Ozymandias | Scrum Master | ART | ART 4 | Team Beta | Watchmen Intrusion | Medium | High
Vision | Product Manager | ART | ART 5 | Team Alpha | Avengers Intelligence | High | High
Hawkeye | Release Train Engineer | ART | ART 5 | Team Alpha | Avengers Intelligence | Medium | High
Scarlet Witch | System Architect | ART | ART 5 | Team Alpha | Avengers Intelligence | Medium | High
Martian Manhunter | Scrum Master | ART | ART 5 | Team Beta | Justice League Analytics | Medium | High
Green Lantern | Scrum Master | ART | ART 5 | Team Beta | Justice League Analytics | Medium | High
Jean Grey | Product Manager | ART | ART 6 | Team Alpha | X-Men Coordination | High | High
Wolverine | Release Train Engineer | ART | ART 6 | Team Alpha | X-Men Coordination | Medium | High
Magneto | System Architect | ART | ART 6 | Team Alpha | X-Men Coordination | Medium | High
Reed Richards | Scrum Master | ART | ART 6 | Team Beta | Fantastic Four Intelligence | Medium | High
Thing | Scrum Master | ART | ART 6 | Team Beta | Fantastic Four Intelligence | Medium | High
Thor | Product Manager | ART | ART 7 | Team Alpha | Avengers Assembly | High | High
Hulk | Release Train Engineer | ART | ART 7 | Team Alpha | Avengers Assembly | Medium | High
Ant-Man | System Architect | ART | ART 7 | Team Alpha | Avengers Assembly | Medium | High
Flash | Scrum Master | ART | ART 7 | Team Beta | Justice League Validation | Medium | High
Aquaman | Scrum Master | ART | ART 7 | Team Beta | Justice League Validation | Medium | High

## Organization
Level | ART | ART Name | Team | Unit | Role | Name | Notes
ART | ART 1 | Ground Control Station | Team Alpha | Justice League Command | Product Manager | Batman
ART | ART 1 | Ground Control Station | Team Alpha | Justice League Command | Release Train Engineer | Superman
ART | ART 1 | Ground Control Station | Team Alpha | Justice League Command | System Architect | Wonder Woman
ART | ART 1 | Ground Control Station | Team Beta | Avengers Interface | Scrum Master | Iron Man
ART | ART 1 | Ground Control Station | Team Beta | Avengers Interface | Scrum Master | Captain America
ART | ART 2 | Airborne Systems | Team Alpha | X-Men Flight | Product Manager | Professor X
ART | ART 2 | Airborne Systems | Team Alpha | X-Men Flight | Release Train Engineer | Cyclops
ART | ART 2 | Airborne Systems | Team Alpha | X-Men Flight | System Architect | Storm
ART | ART 2 | Airborne Systems | Team Beta | Fantastic Four Navigation | Scrum Master | Reed Richards
ART | ART 2 | Airborne Systems | Team Beta | Fantastic Four Navigation | Scrum Master | Sue Storm
ART | ART 3 | Communication Systems | Team Alpha | Teen Titans Communication | Product Manager | Raven
ART | ART 3 | Communication Systems | Team Alpha | Teen Titans Communication | Release Train Engineer | Robin
ART | ART 3 | Communication Systems | Team Alpha | Teen Titans Communication | System Architect | Cyborg
ART | ART 3 | Communication Systems | Team Beta | Guardians of the Network | Scrum Master | Star-Lord
ART | ART 3 | Communication Systems | Team Beta | Guardians of the Network | Scrum Master | Rocket
ART | ART 4 | Security Framework | Team Alpha | S.H.I.E.L.D. Security | Product Manager | Nick Fury
ART | ART 4 | Security Framework | Team Alpha | S.H.I.E.L.D. Security | Release Train Engineer | Black Widow
ART | ART 4 | Security Framework | Team Alpha | S.H.I.E.L.D. Security | System Architect | Doctor Strange
ART | ART 4 | Security Framework | Team Beta | Watchmen Intrusion | Scrum Master | Rorschach
ART | ART 4 | Security Framework | Team Beta | Watchmen Intrusion | Scrum Master | Ozymandias
ART | ART 5 | Data & Analytics | Team Alpha | Avengers Intelligence | Product Manager | Vision
ART | ART 5 | Data & Analytics | Team Alpha | Avengers Intelligence | Release Train Engineer | Hawkeye
ART | ART 5 | Data & Analytics | Team Alpha | Avengers Intelligence | System Architect | Scarlet Witch
ART | ART 5 | Data & Analytics | Team Beta | Justice League Analytics | Scrum Master | Martian Manhunter
ART | ART 5 | Data & Analytics | Team Beta | Justice League Analytics | Scrum Master | Green Lantern
ART | ART 6 | Swarm Coordination | Team Alpha | X-Men Coordination | Product Manager | Jean Grey
ART | ART 6 | Swarm Coordination | Team Alpha | X-Men Coordination | Release Train Engineer | Wolverine
ART | ART 6 | Swarm Coordination | Team Alpha | X-Men Coordination | System Architect | Magneto
ART | ART 6 | Swarm Coordination | Team Beta | Fantastic Four Intelligence | Scrum Master | Reed Richards
ART | ART 6 | Swarm Coordination | Team Beta | Fantastic Four Intelligence | Scrum Master | Thing
ART | ART 7 | Integration & Test | Team Alpha | Avengers Assembly | Product Manager | Thor
ART | ART 7 | Integration & Test | Team Alpha | Avengers Assembly | Release Train Engineer | Hulk
ART | ART 7 | Integration & Test | Team Alpha | Avengers Assembly | System Architect | Ant-Man
ART | ART 7 | Integration & Test | Team Beta | Justice League Validation | Scrum Master | Flash
ART | ART 7 | Integration & Test | Team Beta | Justice League Validation | Scrum Master | Aquaman
ART | ART 1 | Ground Control Station | Team Beta | Avengers Interface | Ui/Ux Developer | Clint Barton
ART | ART 1 | Ground Control Station | Team Beta | Avengers Interface | Ui/Ux Developer | Dane Whitman
ART | ART 1 | Ground Control Station | Team Beta | Avengers Interface | Mission Planning Specialist | Nebula
ART | ART 1 | Ground Control Station | Team Beta | Avengers Interface | Mission Planning Specialist | Yelena Belova
ART | ART 1 | Ground Control Station | Team Beta | Avengers Interface | Real-Time Analytics | Kate Bishop
ART | ART 1 | Ground Control Station | Team Beta | Avengers Interface | Real-Time Analytics | Peter Parker
ART | ART 1 | Ground Control Station | Team Beta | Avengers Interface | Monitoring System Developer | Luke Cage
ART | ART 1 | Ground Control Station | Team Beta | Avengers Interface | Monitoring System Developer | Sam Wilson
ART | ART 2 | Airborne Systems | Team Beta | Fantastic Four Navigation | Ai/Ml Engineer | Gamora
ART | ART 2 | Airborne Systems | Team Beta | Fantastic Four Navigation | Ai/Ml Engineer | Monica Rambeau
ART | ART 2 | Airborne Systems | Team Beta | Fantastic Four Navigation | Computer Vision Specialist | Ben Grimm
ART | ART 2 | Airborne Systems | Team Beta | Fantastic Four Navigation | Computer Vision Specialist | Maria Hill
ART | ART 2 | Airborne Systems | Team Beta | Fantastic Four Navigation | Sensor Integration | Matt Murdock
ART | ART 2 | Airborne Systems | Team Beta | Fantastic Four Navigation | Sensor Integration | Stephen Strange
ART | ART 2 | Airborne Systems | Team Beta | Fantastic Four Navigation | Stealth Technology Developer | Pepper Potts
ART | ART 2 | Airborne Systems | Team Beta | Fantastic Four Navigation | Stealth Technology Developer | Carol Danvers
ART | ART 3 | Communication Systems | Team Beta | Guardians of the Network | Mesh Networking | Jessica Jones
ART | ART 3 | Communication Systems | Team Beta | Guardians of the Network | Mesh Networking | Quake Johnson
ART | ART 3 | Communication Systems | Team Beta | Guardians of the Network | P2P Protocol Developer | Bucky Barnes
ART | ART 3 | Communication Systems | Team Beta | Guardians of the Network | P2P Protocol Developer | Tony Stark
ART | ART 3 | Communication Systems | Team Beta | Guardians of the Network | Long-Range Communication | Frank Castle
ART | ART 3 | Communication Systems | Team Beta | Guardians of the Network | Long-Range Communication | T'Challa
ART | ART 3 | Communication Systems | Team Beta | Guardians of the Network | Satellite Integration Specialist | Steve Rogers
ART | ART 3 | Communication Systems | Team Beta | Guardians of the Network | Satellite Integration Specialist | Shang-Chi
ART | ART 4 | Security Framework | Team Beta | Watchmen Intrusion | Ai-Powered Threat Detection | Rene Ramirez
ART | ART 4 | Security Framework | Team Beta | Watchmen Intrusion | Ai-Powered Threat Detection | Tim Drake
ART | ART 4 | Security Framework | Team Beta | Watchmen Intrusion | Behavioral Analyst Specialist | Helena Bertinelli
ART | ART 4 | Security Framework | Team Beta | Watchmen Intrusion | Behavioral Analyst Specialist | Dinah Lance
ART | ART 4 | Security Framework | Team Beta | Watchmen Intrusion | Incident Response | Stephanie Brown
ART | ART 4 | Security Framework | Team Beta | Watchmen Intrusion | Incident Response | Kendra Saunders
ART | ART 4 | Security Framework | Team Beta | Watchmen Intrusion | Threat Mitigation Specialist | Mari McCabe
ART | ART 4 | Security Framework | Team Beta | Watchmen Intrusion | Threat Mitigation Specialist | Victor Zsasz
ART | ART 5 | Data & Analytics | Team Beta | Justice League Analytics | Data Pipeline Engineer | Carter Hall
ART | ART 5 | Data & Analytics | Team Beta | Justice League Analytics | Data Pipeline Engineer | John Stewart
ART | ART 5 | Data & Analytics | Team Beta | Justice League Analytics | Etl Specialist | Zatanna Zatara
ART | ART 5 | Data & Analytics | Team Beta | Justice League Analytics | Etl Specialist | Kaldur'ahm
ART | ART 5 | Data & Analytics | Team Beta | Justice League Analytics | Business Intelligence | Ryan Choi
ART | ART 5 | Data & Analytics | Team Beta | Justice League Analytics | Business Intelligence | Donna Troy
ART | ART 5 | Data & Analytics | Team Beta | Justice League Analytics | Data Visualization Specialist | Eobard Thawne
ART | ART 5 | Data & Analytics | Team Beta | Justice League Analytics | Data Visualization Specialist | Barbara Gordon
ART | ART 6 | Swarm Coordination | Team Beta | Fantastic Four Intelligence | Machine Learning Engineer | Shuri
ART | ART 6 | Swarm Coordination | Team Beta | Fantastic Four Intelligence | Machine Learning Engineer | Danny Rand
ART | ART 6 | Swarm Coordination | Team Beta | Fantastic Four Intelligence | Algorithm Specialist | Johnny Storm
ART | ART 6 | Swarm Coordination | Team Beta | Fantastic Four Intelligence | Algorithm Specialist | Bruce Banner
ART | ART 6 | Swarm Coordination | Team Beta | Fantastic Four Intelligence | Swarm Behavior Specialist | Groot
ART | ART 6 | Swarm Coordination | Team Beta | Fantastic Four Intelligence | Swarm Behavior Specialist | Okoye
ART | ART 6 | Swarm Coordination | Team Beta | Fantastic Four Intelligence | Formation Control Engineer | Hank Pym
ART | ART 6 | Swarm Coordination | Team Beta | Fantastic Four Intelligence | Formation Control Engineer | Jennifer Walters
ART | ART 7 | Integration & Test | Team Beta | Justice League Validation | System Integration Engineer | Rory Regan
ART | ART 7 | Integration & Test | Team Beta | Justice League Validation | System Integration Engineer | Huntress Wayne
ART | ART 7 | Integration & Test | Team Beta | Justice League Validation | Interface Testing Specialist | Oliver Queen
ART | ART 7 | Integration & Test | Team Beta | Justice League Validation | Interface Testing Specialist | Ravager Wilson
ART | ART 7 | Integration & Test | Team Beta | Justice League Validation | End-To-End Testing | Cassandra Cain
ART | ART 7 | Integration & Test | Team Beta | Justice League Validation | End-To-End Testing | Kara Zor-El
ART | ART 7 | Integration & Test | Team Beta | Justice League Validation | Validation Specialist | Wally West
ART | ART 7 | Integration & Test | Team Beta | Justice League Validation | Validation Specialist | Talia al Ghul

## Teams
ART | Team | Unit | Role | Count
ART 1 | Team Alpha | Justice League Command | Product Manager | 1
ART 1 | Team Alpha | Justice League Command | Release Train Engineer | 1
ART 1 | Team Alpha | Justice League Command | System Architect | 1
ART 1 | Team Beta | Avengers Interface | Mission Planning Specialist | 2
ART 1 | Team Beta | Avengers Interface | Monitoring System Developer | 2
ART 1 | Team Beta | Avengers Interface | Real-Time Analytics | 2
ART 1 | Team Beta | Avengers Interface | Scrum Master | 2
ART 1 | Team Beta | Avengers Interface | Ui/Ux Developer | 2
ART 2 | Team Alpha | X-Men Flight | Product Manager | 1
ART 2 | Team Alpha | X-Men Flight | Release Train Engineer | 1
ART 2 | Team Alpha | X-Men Flight | System Architect | 1
ART 2 | Team Beta | Fantastic Four Navigation | Ai/Ml Engineer | 2
ART 2 | Team Beta | Fantastic Four Navigation | Computer Vision Specialist | 2
ART 2 | Team Beta | Fantastic Four Navigation | Scrum Master | 2
ART 2 | Team Beta | Fantastic Four Navigation | Sensor Integration | 2
ART 2 | Team Beta | Fantastic Four Navigation | Stealth Technology Developer | 2
ART 3 | Team Alpha | Teen Titans Communication | Product Manager | 1
ART 3 | Team Alpha | Teen Titans Communication | Release Train Engineer | 1
ART 3 | Team Alpha | Teen Titans Communication | System Architect | 1
ART 3 | Team Beta | Guardians of the Network | Long-Range Communication | 2
ART 3 | Team Beta | Guardians of the Network | Mesh Networking | 2
ART 3 | Team Beta | Guardians of the Network | P2P Protocol Developer | 2
ART 3 | Team Beta | Guardians of the Network | Satellite Integration Specialist | 2
ART 3 | Team Beta | Guardians of the Network | Scrum Master | 2
ART 4 | Team Alpha | S.H.I.E.L.D. Security | Product Manager | 1
ART 4 | Team Alpha | S.H.I.E.L.D. Security | Release Train Engineer | 1
ART 4 | Team Alpha | S.H.I.E.L.D. Security | System Architect | 1
ART 4 | Team Beta | Watchmen Intrusion | Ai-Powered Threat Detection | 2
ART 4 | Team Beta | Watchmen Intrusion | Behavioral Analyst Specialist | 2
ART 4 | Team Beta | Watchmen Intrusion | Incident Response | 2
ART 4 | Team Beta | Watchmen Intrusion | Scrum Master | 2
ART 4 | Team Beta | Watchmen Intrusion | Threat Mitigation Specialist | 2
ART 5 | Team Alpha | Avengers Intelligence | Product Manager | 1
ART 5 | Team Alpha | Avengers Intelligence | Release Train Engineer | 1
ART 5 | Team Alpha | Avengers Intelligence | System Architect | 1
ART 5 | Team Beta | Justice League Analytics | Business Intelligence | 2
ART 5 | Team Beta | Justice League Analytics | Data Pipeline Engineer | 2
ART 5 | Team Beta | Justice League Analytics | Data Visualization Specialist | 2
ART 5 | Team Beta | Justice League Analytics | Etl Specialist | 2
ART 5 | Team Beta | Justice League Analytics | Scrum Master | 2
ART 6 | Team Alpha | X-Men Coordination | Product Manager | 1
ART 6 | Team Alpha | X-Men Coordination | Release Train Engineer | 1
ART 6 | Team Alpha | X-Men Coordination | System Architect | 1
ART 6 | Team Beta | Fantastic Four Intelligence | Algorithm Specialist | 2
ART 6 | Team Beta | Fantastic Four Intelligence | Formation Control Engineer | 2
ART 6 | Team Beta | Fantastic Four Intelligence | Machine Learning Engineer | 2
ART 6 | Team Beta | Fantastic Four Intelligence | Scrum Master | 2
ART 6 | Team Beta | Fantastic Four Intelligence | Swarm Behavior Specialist | 2
ART 7 | Team Alpha | Avengers Assembly | Product Manager | 1
ART 7 | Team Alpha | Avengers Assembly | Release Train Engineer | 1
ART 7 | Team Alpha | Avengers Assembly | System Architect | 1
ART 7 | Team Beta | Justice League Validation | End-To-End Testing | 2
ART 7 | Team Beta | Justice League Validation | Interface Testing Specialist | 2
ART 7 | Team Beta | Justice League Validation | Scrum Master | 2
ART 7 | Team Beta | Justice League Validation | System Integration Engineer | 2
ART 7 | Team Beta | Justice League Validation | Validation Specialist | 2

## Activities
ID | Title | Team | ART | Assigned To | Role | Sprint | Estimate (h) | Status | Priority | Dependency
A-001 | GCS-Airborne interface contract | Justice League Command | ART 1 | Batman | Product Manager | Sprint 1 | 6 | Planned | High | Professor X
A-002 | Secure comms requirement baseline | Teen Titans Communication | ART 3 | Raven | Product Manager | Sprint 2 | 8 | Planned | High | Nick Fury
A-003 | Swarm/Flight behavior API | X-Men Coordination | ART 6 | Jean Grey | Product Manager | Sprint 2 | 10 | Planned | High | Professor X
A-004 | Integration test plan v1 | Avengers Assembly | ART 7 | Thor | Product Manager | Sprint 1 | 12 | Planned | High | ALL

## RACI
Activity | Zeus | Athena | Hermes | M | Q | Moneypenny | Product Managers | RTEs | System Architects | Scrum Masters
PI Planning (Portfolio) | A | C | I | R | C | I | C | I | I | I
Solution PI Planning | I | C | I | A | C | R | C | R | C | I
Architecture Sync | I | A | I | C | R | I | I | I | R | I
Monthly Stakeholder Review | A | C | R | I | I | R | C | I | I | I
Solution Demo | I | I | I | A | C | R | R | R | C | C
Security Review | I | C | I | C | C | I | C | I | R | I

## Risks_Issues
ID | Type | Title | Description | Owner | Impact | Probability | Mitigation | Status | Target Sprint

## Resource_Workload
Resource | Role | Level | ART | Team | Unit | Cap Hrs/Sprint | S1 % | S2 % | S3 % | S4 % | S5 % | S6 % | S7 % | S8 % | S1 Hrs | S2 Hrs | S3 Hrs | S4 Hrs | S5 Hrs | S6 Hrs | S7 Hrs | S8 Hrs | Total Hrs | Avg Util % | Over/Under Hrs
Batman | Product Manager | ART | ART 1 | Team Alpha | Justice League Command | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Superman | Release Train Engineer | ART | ART 1 | Team Alpha | Justice League Command | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Wonder Woman | System Architect | ART | ART 1 | Team Alpha | Justice League Command | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Iron Man | Scrum Master | ART | ART 1 | Team Beta | Avengers Interface | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Captain America | Scrum Master | ART | ART 1 | Team Beta | Avengers Interface | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Professor X | Product Manager | ART | ART 2 | Team Alpha | X-Men Flight | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Cyclops | Release Train Engineer | ART | ART 2 | Team Alpha | X-Men Flight | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Storm | System Architect | ART | ART 2 | Team Alpha | X-Men Flight | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Reed Richards | Scrum Master | ART | ART 2 | Team Beta | Fantastic Four Navigation | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Sue Storm | Scrum Master | ART | ART 2 | Team Beta | Fantastic Four Navigation | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Raven | Product Manager | ART | ART 3 | Team Alpha | Teen Titans Communication | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Robin | Release Train Engineer | ART | ART 3 | Team Alpha | Teen Titans Communication | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Cyborg | System Architect | ART | ART 3 | Team Alpha | Teen Titans Communication | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Star-Lord | Scrum Master | ART | ART 3 | Team Beta | Guardians of the Network | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Rocket | Scrum Master | ART | ART 3 | Team Beta | Guardians of the Network | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Nick Fury | Product Manager | ART | ART 4 | Team Alpha | S.H.I.E.L.D. Security | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Black Widow | Release Train Engineer | ART | ART 4 | Team Alpha | S.H.I.E.L.D. Security | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Doctor Strange | System Architect | ART | ART 4 | Team Alpha | S.H.I.E.L.D. Security | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Rorschach | Scrum Master | ART | ART 4 | Team Beta | Watchmen Intrusion | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Ozymandias | Scrum Master | ART | ART 4 | Team Beta | Watchmen Intrusion | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Vision | Product Manager | ART | ART 5 | Team Alpha | Avengers Intelligence | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Hawkeye | Release Train Engineer | ART | ART 5 | Team Alpha | Avengers Intelligence | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Scarlet Witch | System Architect | ART | ART 5 | Team Alpha | Avengers Intelligence | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Martian Manhunter | Scrum Master | ART | ART 5 | Team Beta | Justice League Analytics | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Green Lantern | Scrum Master | ART | ART 5 | Team Beta | Justice League Analytics | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Jean Grey | Product Manager | ART | ART 6 | Team Alpha | X-Men Coordination | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Wolverine | Release Train Engineer | ART | ART 6 | Team Alpha | X-Men Coordination | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Magneto | System Architect | ART | ART 6 | Team Alpha | X-Men Coordination | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Reed Richards | Scrum Master | ART | ART 6 | Team Beta | Fantastic Four Intelligence | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Thing | Scrum Master | ART | ART 6 | Team Beta | Fantastic Four Intelligence | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Thor | Product Manager | ART | ART 7 | Team Alpha | Avengers Assembly | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Hulk | Release Train Engineer | ART | ART 7 | Team Alpha | Avengers Assembly | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Ant-Man | System Architect | ART | ART 7 | Team Alpha | Avengers Assembly | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Flash | Scrum Master | ART | ART 7 | Team Beta | Justice League Validation | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Aquaman | Scrum Master | ART | ART 7 | Team Beta | Justice League Validation | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Clint Barton | Ui/Ux Developer | ART | ART 1 | Team Beta | Avengers Interface | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Dane Whitman | Ui/Ux Developer | ART | ART 1 | Team Beta | Avengers Interface | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Nebula | Mission Planning Specialist | ART | ART 1 | Team Beta | Avengers Interface | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Yelena Belova | Mission Planning Specialist | ART | ART 1 | Team Beta | Avengers Interface | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Kate Bishop | Real-Time Analytics | ART | ART 1 | Team Beta | Avengers Interface | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Peter Parker | Real-Time Analytics | ART | ART 1 | Team Beta | Avengers Interface | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Luke Cage | Monitoring System Developer | ART | ART 1 | Team Beta | Avengers Interface | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Sam Wilson | Monitoring System Developer | ART | ART 1 | Team Beta | Avengers Interface | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Gamora | Ai/Ml Engineer | ART | ART 2 | Team Beta | Fantastic Four Navigation | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Monica Rambeau | Ai/Ml Engineer | ART | ART 2 | Team Beta | Fantastic Four Navigation | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Ben Grimm | Computer Vision Specialist | ART | ART 2 | Team Beta | Fantastic Four Navigation | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Maria Hill | Computer Vision Specialist | ART | ART 2 | Team Beta | Fantastic Four Navigation | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Matt Murdock | Sensor Integration | ART | ART 2 | Team Beta | Fantastic Four Navigation | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Stephen Strange | Sensor Integration | ART | ART 2 | Team Beta | Fantastic Four Navigation | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Pepper Potts | Stealth Technology Developer | ART | ART 2 | Team Beta | Fantastic Four Navigation | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Carol Danvers | Stealth Technology Developer | ART | ART 2 | Team Beta | Fantastic Four Navigation | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Jessica Jones | Mesh Networking | ART | ART 3 | Team Beta | Guardians of the Network | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Quake Johnson | Mesh Networking | ART | ART 3 | Team Beta | Guardians of the Network | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Bucky Barnes | P2P Protocol Developer | ART | ART 3 | Team Beta | Guardians of the Network | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Tony Stark | P2P Protocol Developer | ART | ART 3 | Team Beta | Guardians of the Network | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Frank Castle | Long-Range Communication | ART | ART 3 | Team Beta | Guardians of the Network | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
T'Challa | Long-Range Communication | ART | ART 3 | Team Beta | Guardians of the Network | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Steve Rogers | Satellite Integration Specialist | ART | ART 3 | Team Beta | Guardians of the Network | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Shang-Chi | Satellite Integration Specialist | ART | ART 3 | Team Beta | Guardians of the Network | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Rene Ramirez | Ai-Powered Threat Detection | ART | ART 4 | Team Beta | Watchmen Intrusion | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Tim Drake | Ai-Powered Threat Detection | ART | ART 4 | Team Beta | Watchmen Intrusion | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Helena Bertinelli | Behavioral Analyst Specialist | ART | ART 4 | Team Beta | Watchmen Intrusion | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Dinah Lance | Behavioral Analyst Specialist | ART | ART 4 | Team Beta | Watchmen Intrusion | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Stephanie Brown | Incident Response | ART | ART 4 | Team Beta | Watchmen Intrusion | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Kendra Saunders | Incident Response | ART | ART 4 | Team Beta | Watchmen Intrusion | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Mari McCabe | Threat Mitigation Specialist | ART | ART 4 | Team Beta | Watchmen Intrusion | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Victor Zsasz | Threat Mitigation Specialist | ART | ART 4 | Team Beta | Watchmen Intrusion | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Carter Hall | Data Pipeline Engineer | ART | ART 5 | Team Beta | Justice League Analytics | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
John Stewart | Data Pipeline Engineer | ART | ART 5 | Team Beta | Justice League Analytics | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Zatanna Zatara | Etl Specialist | ART | ART 5 | Team Beta | Justice League Analytics | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Kaldur'ahm | Etl Specialist | ART | ART 5 | Team Beta | Justice League Analytics | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Ryan Choi | Business Intelligence | ART | ART 5 | Team Beta | Justice League Analytics | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Donna Troy | Business Intelligence | ART | ART 5 | Team Beta | Justice League Analytics | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Eobard Thawne | Data Visualization Specialist | ART | ART 5 | Team Beta | Justice League Analytics | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Barbara Gordon | Data Visualization Specialist | ART | ART 5 | Team Beta | Justice League Analytics | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Shuri | Machine Learning Engineer | ART | ART 6 | Team Beta | Fantastic Four Intelligence | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Danny Rand | Machine Learning Engineer | ART | ART 6 | Team Beta | Fantastic Four Intelligence | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Johnny Storm | Algorithm Specialist | ART | ART 6 | Team Beta | Fantastic Four Intelligence | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Bruce Banner | Algorithm Specialist | ART | ART 6 | Team Beta | Fantastic Four Intelligence | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Groot | Swarm Behavior Specialist | ART | ART 6 | Team Beta | Fantastic Four Intelligence | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Okoye | Swarm Behavior Specialist | ART | ART 6 | Team Beta | Fantastic Four Intelligence | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Hank Pym | Formation Control Engineer | ART | ART 6 | Team Beta | Fantastic Four Intelligence | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Jennifer Walters | Formation Control Engineer | ART | ART 6 | Team Beta | Fantastic Four Intelligence | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Rory Regan | System Integration Engineer | ART | ART 7 | Team Beta | Justice League Validation | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Huntress Wayne | System Integration Engineer | ART | ART 7 | Team Beta | Justice League Validation | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Oliver Queen | Interface Testing Specialist | ART | ART 7 | Team Beta | Justice League Validation | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Ravager Wilson | Interface Testing Specialist | ART | ART 7 | Team Beta | Justice League Validation | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Cassandra Cain | End-To-End Testing | ART | ART 7 | Team Beta | Justice League Validation | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Kara Zor-El | End-To-End Testing | ART | ART 7 | Team Beta | Justice League Validation | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Wally West | Validation Specialist | ART | ART 7 | Team Beta | Justice League Validation | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0
Talia al Ghul | Validation Specialist | ART | ART 7 | Team Beta | Justice League Validation | 65 | S1 %: 0; S2 %: 0; S3 %: 0; S4 %: 0; S5 %: 0; S6 %: 0; S7 %: 0; S8 %: 0

## Summary_ART
ART | Headcount | Total Cap/Sprint | S1 Hrs | S2 Hrs | S3 Hrs | S4 Hrs | S5 Hrs | S6 Hrs | S7 Hrs | S8 Hrs | Total Hrs | Overall Util % | Avg Util % | Over/Under Hrs
ART 1
ART 2
ART 3
ART 4
ART 5
ART 6
ART 7

## Summary_Team
ART | Team | Unit | Headcount | Total Cap/Sprint | S1 Hrs | S2 Hrs | S3 Hrs | S4 Hrs | S5 Hrs | S6 Hrs | S7 Hrs | S8 Hrs | Total Hrs | Overall Util % | Avg Util % | Over/Under Hrs
ART 1 | Team Alpha | Justice League Command
ART 1 | Team Beta | Avengers Interface
ART 2 | Team Alpha | X-Men Flight
ART 2 | Team Beta | Fantastic Four Navigation
ART 3 | Team Alpha | Teen Titans Communication
ART 3 | Team Beta | Guardians of the Network
ART 4 | Team Alpha | S.H.I.E.L.D. Security
ART 4 | Team Beta | Watchmen Intrusion
ART 5 | Team Alpha | Avengers Intelligence
ART 5 | Team Beta | Justice League Analytics
ART 6 | Team Alpha | X-Men Coordination
ART 6 | Team Beta | Fantastic Four Intelligence
ART 7 | Team Alpha | Avengers Assembly
ART 7 | Team Beta | Justice League Validation

## Dashboard
Metric | Value
Total Resources
Avg Utilization (all)
Overutilized Count (>1.0 avg)